## Sprint Planning
TASK NAME | DAY | STATUS | DURATION(in days)
Sprint 1 |  | In Progress | 4
DB Creation | Monday | Complete | 1
Project Setup | Tuesday | Not Started | 1
Login Page/User Authentication | Tuesday, Wednesday | Not Started | 2
Home Page Design | Thursday | Not Started | 1